## Instructions
DOMAIN NAME: | Data Analytics
PROJECT MEMBER NAME: | Makarand Ramakant Jena
PROJECT NAME: | Intern Letter Portal
DOCUMENT NAME: | Lessons Learnt Log
CREATED ON: | 2025-12-30
Purpose of Document
Lessons Learned Logs are used to capture and share knowledge about what has worked well and what could have been done differently during the planning, management and delivery of an improvement project.
They help others learn from the project team's experience. Lesson Learned Logs: Help support a learning culture.

## LESSONS LEARNED
LESSONS LEARNED
DOCUMENT VERSION: 1.0
PROJECT NAME | Intern Letter Portal
PROJECT ID | NA
PROJECT MANAGER | Ms. Harshada Topale
PROJECT SPONSOR | Mr. Tushar Topale
SL. NO | DATE RAISED | EVENT | LESSON CATEGORY | EARLY WARNING SIGNS? | RECOMMENDATIONS | ACTIONS | OWNER | STATUS | ADDITIONAL COMMENTS
1 | 2025-12-16 | Sample test certificates were accidentally delivered to interns | Process / Governance | Test artifacts mixed with production workflows | Separate test and production flows clearly; restrict test certificate generation | Shifted official letters to Intern Letter Portal with controlled access | Team | Closed | Triggered the need for a centralized, authenticated portal
2 | 2025-12-17 | Duplicate Appointment Letter submissions attempted by users | Functional Design | Same user attempting to resubmit form | Enforce single-submission logic at backend | Added record existence check and blocking dialog | System | Closed | Improved data integrity and user guidance
3 | 2025-12-17 | Authentication failures due to incorrect profile data | Data Quality | Multiple login failures from valid users | Validate profile data at source; improve help text | Clarified login instructions and restricted sheet access | Admin | Closed | Reduced support requests
4 | 2025-12-18 | Users unclear why Experience Letter download was disabled | UX / Communication | Repeated queries from interns | Display reason-specific messages instead of generic denial | Added customized eligibility messages | Team | Closed | Improved transparency and reduced confusion
5 | 2025-12-18 | Interns completed projects in multiple domains | Functional Coverage | Only one record shown per Intern ID | Support multiple records per Intern ID | Modified UI to display multiple records sequentially | Team | Closed | Improved completeness of experience reporting
6 | 2025-12-19 | Risk of unauthorized access to generated PDFs | Security | Shared Drive links without restriction | Enforce view-only access and permission checks | Applied least-privilege Drive permissions | Admin | Closed | Ensured document confidentiality
7 | 2025-12-20 | Users expected to edit submitted form details | UX / Policy | Requests for post-submission edits | Clearly communicate one-time submission policy | Locked form after submission and added warning text | System | Closed | Reduced inconsistencies in issued letters
8 | 2025-12-20 | Delay in Experience Letter availability due to pending verification | Process Dependency | Sheets not updated by Domain Leads | Define clear SOPs and ownership | Assigned responsibility to Domain Leads for timely updates | Admin / Domain Leads | Closed | Highlighted importance of role clarity
9 | 2025-12-21 | Reliance on Google Sheets and Drive availability | Infrastructure | Temporary access delays | Add graceful error handling and admin alerts | Implemented user-friendly error messages | System | Closed | Platform dependency accepted
10 | 2025-12-22 | Managing separate apps increased complexity | Architecture | Duplicate logic across apps | Integrate modules under a unified portal | Created Intern Letter Portal with shared auth | Team | Closed | Simplified maintenance and scalability