## RAID LOG
RAID Log | [8 empty] | Total | Critical | High | Moderate | Low | Negligible
[8 empty] | Risk | 5 | 0 | 0 | 0 | 0 | 0
Project title: | Intern Letter Portal |  | Project Id: | NA | Project Manager: | Harshada Topale |  | Assumption | 4 | 0 | 0 | 0 | 0 | 0
[8 empty] | Issue | 4 | 0 | 0 | 0 | 0 | 0
DOCUMENT VERSION: | 1 |  | Last Updated date: | 2025-12-22 | Project Team Lead: | Makarand Jena |  | Dependency | 5 | 0 | 0 | 0 | 0 | 0
Select … |  |  |  |  | Select … | Risk Priority Number | Open/Closed |  | 18 |  |  |  |  | 0
RAID Category | Description | Impact | Mitigation | Owner | Priority | RPN (for risks) | Status
Risk | Incorrect or missing user credentials in IAC Profile Sheet (logins fail or wrong users granted access) | High | Validate profile data before granting access; restrict sheet edits to admins; input validation and periodic data audit | Admin | High | 24 | Closed
Risk | Duplicate Appointment Letter generation (same user gets multiple letters / folders) | Medium | Enforce single-entry check in GPI New Joinee workbook; block duplicate submissions; show informative dialog | System | Medium | 12 | Closed
Risk | Unauthorized access to letters (improper Drive/Sheet permissions) | High | Enforce sheet-based auth, least-privilege Drive permissions, view-only links for users, periodic permission review | System / Admin | High | 20 | Closed
Risk | Incorrect eligibility logic for Experience Letter (bugs in checks: considerforexperienceletter / verification) | High | Implement unit tests, code review, staging validation, automated test cases for business rules | System / Dev | High | 30 | Closed
Risk | Google Sheets or Drive service outage (unavailable backend) | High | Graceful error handling, user-friendly outage messages, retry/backoff logic, admin alerts | Admin / System | High | 20 | Closed
Assumption | Users submit correct email ID and mobile number in IAC Profile Form | Medium | Validate input at submission; periodic data cleansing; communicate format to users | Admin | Medium | N/A | Closed
Assumption | Domain Leads update project status accurately and in a timely manner | High | Send update reminders to Domain Leads; provide clear update SOPs; audit edits | Domain Leads | High | N/A | Closed
Assumption | Users will not need to modify form details after submission (form locked) | Medium | Communicate “one-time submission” policy clearly in UI/help text; provide admin edit path for fixes | System / Admin | Medium | N/A | Closed
Assumption | Google Workspace services remain available and stable | High | Monitor Google service status; maintain incident response plan | Admin | High | N/A | Closed
Issue | Sample test certificates accidentally delivered earlier (process gap) | High | Moved certificate issuance to Intern Letter Portal; tightened release process | Team | High | N/A | Closed
Issue | Multiple project domains per intern not initially supported | Medium | Modified Experience Letter app to display multiple records and allow per-record download where applicable | Team | Medium | N/A | Closed
Issue | Users attempting repeated/duplicate form submissions | Low | Added duplicate check and blocking dialog; improved messaging | System | Low | N/A | Closed
Issue | Users unaware of eligibility conditions for Experience Letter | Medium | Show specific status messages explaining why download is disabled; add help text / FAQ | Team | Medium | N/A | Closed
Dependency | Google Apps Script (core backend execution) | High | Maintain versioned scripts, use test/staging deployments, code reviews | Google Platform / Dev | High | N/A | Closed
Dependency | Google Sheets (auth, intern data, project status) | High | Backup sheets regularly; restrict edit permissions; document sheet schema | Admin | High | N/A | Closed
Dependency | Google Drive (storage of generated PDFs) | High | Organize folders with consistent permissions; monitor quotas; backup critical files | Admin | High | N/A | Closed
Dependency | IAC Website (embedded link / access point) | Medium | Coordinate with IAC team for correct embedding and link updates; QA before publish | IAC Team | Medium | N/A | Closed
Dependency | Domain Leads (updates to verification / eligibility fields) | High | Provide SOP and reminders; grant controlled edit access; audit logs | Domain Leads | High | N/A | Closed